## Project Description
Your Name: | Phoebe Huang
Project Description:
A small flight simulator in a inverted planet environment

## User Stories
User Stories
UserStory# | StoryName | As a … | I want… | So That… | Status
1 | LoadSphere | User | Load inverted sphere model with ocean texture | I can load other props | Completed
2 | LoadModel | User | Load other props inside sphere | I can populate scene | Completed
3 | LoadInstructions | User | Load in text instructions | I know what to do | Completed(ish)
4 | LoadCharacter | User | Load player model | I have an object representing me in the scene | Completed
5 | ImplementControls | User | Implement FPS flight controls | I can manipulate player model | Completed
6 | AddSound | User | Add SFX and/or music loop | I can hear sound feedback and/or ambiance | In-Progress
7 | AddBoundary | User | A boundary preventing me to leave outside of the intended space. | I won't be able to leave the intended area | Completed
8 | FinishApp | User | Notify end of app | To exit app | In-Progress
9 | ImplementOcean | User | Add rolling ocean texture | I can perceive the enclosing sphere as an ocean | In-Progress

## Backlog
Backlog |  |  | (Bug or Task)
Priority | BacklogId | StoryName | BacklogType | Description | In | InSprint | Column1
1 | 1 | LoadSphere | Task | Load inverted sphere model with ocean texture | JSExperiment.Init() | 1 | Completed
1 | 5 | ImplementControls | Task | Implement FPS flight controls |  | 1 | Completed
1 | 8 | AddBoundary | Task | A boundary preventing me to leave outside of the intended space. |  | 1 | Completed
2 | 3 | LoadModel | Task | Load other props inside sphere | JSExperiment.Init() | 3 | Completed
2 | 4 | LoadCharacter | Task | Load player model | JSExperiment.Init() | 3 | Completed
2 | 7 | FixCanvasScaling | Bug | Fix canvas to scale with browser |  | 1 | Completed
3 | 2 | LoadInstructions | Task | Load in text instructions | Html.html | 3 | Completed
3 | 10 | ImplementOcean | Task | Add rolling ocean texture | JSExperiment.Init() | 4 | Completed
4 | 6 | AddSound | Task | Add SFX/music | JSExperiment.Init() | 4 | Completed
4 | 9 | FinishApp | Task | Notify end of app |  | 4 | Discarded

## Sprint1_11-19
Sprint 1
Points | BacklogId | StoryName | BacklogType | Description | In | Column1
7 | 1 | LoadSphere | Task | Load inverted sphere model with ocean texture | JSExperiment.Init() | Completed
8 | 3 | ImplementControls | Task | Implement FPS flight controls | JSExperiment.Init() | Completed
8 | 2 | AddBoundary | Task | A boundary preventing me to leave outside of the intended space. | JSExperiment.Init() | Completed
4 | 7 | FixCanvasScaling | Bug | Fix canvas to scale with browser | JSExperiment.Init() | Completed
Link to Branch: |  | https://github.com/Kuroshi117/GraphApp.git
Notes from Review:

## Sprint2_11-26
Sprint 2
Points | BacklogId | StoryName | BacklogType | Description | In | Column1
7 | 3 | LoadModel | Task | Load other props inside sphere | JSExperiment.Init() | In-Progress
5 | 4 | LoadCharacter | Task | Load player model | JSExperiment.Init() | In-Progress
Link to Branch: |  | https://github.com/Kuroshi117/GraphApp/tree/Sprint2
Notes from Review:

## Sprint3_12-3
Sprint 3
Points | BacklogId | StoryName | BacklogType | Description | In | Column1
7 | 3 | LoadModel(cont.) | Task | Load other props inside sphere | JSExperiment.Init() | Completed
5 | 4 | LoadCharacter(cont.) | Task | Load player model | JSExperiment.Init() | Completed
3 | 2 | LoadInstructions | Task | Load in text instructions | Html.html | Completed(ish)
2 | 6 | AddSound | Task | Add SFX/music | JSExperiment.Init() | In-Progress
2 | 9 | FinishApp | Task | Notify end of app |  | In-Progress
Link to Branch: |  | https://github.com/Kuroshi117/GraphApp/tree/Sprint3
Notes from Review:

## Release
Release
Points | BacklogId | StoryName | BacklogType | Description | In | Column1
4 | 6 | AddSound(cont.) | Task | Add SFX/music | JSExperiment.Init() | Completed
2 | 9 | FinishApp(cont.) | Task | Notify end of app |  | Discarded
6 | 10 | ImplementOcean | Task | Add rolling ocean texture | JSExperiment.Init() | Completed
Link to Branch: |  | https://github.com/Kuroshi117/GraphApp/tree/Final
AFTER SHIPPING, REVIEW MAIN BACKLOG AND MARK STATUS
Notes from Review: